## PALO Accpac
Please enter the deadline for solving your allocation issue.
SL | Status | Date of Issue Raised | Date of Issue Handover | Date of Issue Solved | Date of Issue ReSolved | Issue | Priority | Issue Type | Solved By | Responsible Person | Issue Raised By- Business User | Time
2 | Done | 2023-12-28 |  |  |  | Accpac customer (12104-4524) is not auto synchronized in ABOM | High | Technical |  | Salman | Mr. Haque
3 | Done | 2023-12-28 |  |  |  | Circulation bill archiving data exe create but user side network issue (new created in micro) | High | Functional |  | Afrin+Mamun | Mr. Haque
4 | Done | 2023-12-28 |  |  |  | RPT- 00174033 status synchronized in ABOM but shown due in ACCPAC | High |  |  | Salman | Mr. Haque
5 | Done | 2023-12-28 |  | 2024-01-15 |  | Credit booking showed as run time error during synchronizing - ABOM issue (Check mail in details) | High |  |  | Salman | Mr. Haque
6 | Done | 2024-01-04 |  | 2024-01-11 |  | Surjo IO-24011033078 shown in middle db but not shown in accpac | High
7 | Done | 2024-01-13 |  | 2024-01-16 |  | 31st December, 2023 Credit receipt showed as run time error during synchronizing-ABOM issue (Check mail in details) | High |  |  | Salman | Mr. Haque
8 | Done | 2024-01-14 |  |  |  | Order entry, Shipment, Invoice, Purchase order accpac year end issue | High |  |  | Jitu | Mr. Haque
9 | Done | 2024-01-16 |  | 2024-01-21 |  | Yearly Increment for-2024 Changes in Norming Payroll as per PALO Management has finalized | High |  | Mr.Tawhid+Mamun+Amir Hamza | Jitu | Mr. Haque
10 | Done | 2024-01-31 | 2024-02-01 | 2024-02-06 |  | 28th January, 2024 Credit receipt showed as run time error during synchronizing-ABOM issue (Check mail in details) | High |  |  | Salman | Mr. Haque | User End Network issue
11 | Done | 2023-12-04 | 2024-02-11 |  |  | Incorporate new Bank Code & Distribution Code for Prothoma Ambarkhana Sylhet | High |  |  | Jitu | Mr. Haque
12 | Done | 2024-02-13 | 2024-02-13 | 2024-02-15 |  | Accounts Section Data Center & Accpac Access create new user-Abom issue (Check mail in details) | High |  |  | Jitu | Mr. Haque
13 | Done | 2024-02-13 | 2024-02-13 | 2024-02-15 |  | AR customer outstanding invoice not found in 3.33 server maping the server (Check whatsapp) | High |  |  | Jitu | Mr. Haque
14 | Done | 2024-03-19 | 2024-04-02 |  |  | 3rd March, 2024 Credit receipt showed as a run time error during synchronizing-ABOM issue (Check mail in details) | High | Functional | Jitu | Afrin+Mamun | Mr. Haque
15 | Done | 2024-03-19 | 2024-04-02 | 2024-04-16 |  | 4rd March, 2024 Credit receipt showed as a run time error during synchronizing-ABOM issue (Check mail in details) | High |  | Afrin |  | Mr. Haque
16 | Done | 2024-04-06 |  | 2024-04-25 |  | 24th March, 2024 Credit receipt showed as a run time error during synchronizing-ABOM issue (Check mail in details) | High | Technical | Ridwan | Afrin | Mr. Haque | Not found due ammount
17 | Done | 2024-04-09 |  |  |  | 31th March, 2024 Credit receipt showed as a run time error during synchronizing-ABOM issue (Check mail in details)
18 | Done | 2024-05-08 |  | 2024-05-08 |  | Incorporated the GL Head in ACCPAC Print Media " BBL 2nd Subordinated Bond | High | Functional | Tawhid Sir | Amir Hamza | Mr.Haque
19 | Done | 2024-05-08 |  | 2024-05-22 |  | create the following user in ACCPAC-APPSVR01 as well as ACCPAC-APPSVR02. His permission access Entry Level AP, AR, GL.(Check mail in details) | High | Functional | Jitu | Amir Hamza | Mr.Haque
20 | Done | 2024-05-20 |  | 2024-05-26 |  | create the following users in ACCPAC-APPSVR01 as well as ACCPAC-APPSVR02 as soon as possible. His permission access Entry Level AP & PO | High | Functional | Amir Hamza | Amir Hamza | Mr.Haque
21 | Done | 2024-05-20 |  | 2024-05-26 |  | Abom Micro syncronizing cash receipt 14 may run time error | High | tecnical | Hamza bin Habibur | Amir Hamza | Mr.Haque
22 | Done | 2024-06-10 |  | 2024-06-13 |  | GL batch listing crystal report viwer log in failed | High | tecnical | Hamza bin Habibur | Amir Hamza | Mr.Haque
23 | Done | 2024-06-11 |  | 2024-06-13 |  | AIT & TDS macro syncronizing run time error issue | High | tecnical | Hamza bin Habibur | Amir Hamza | Mr.Haque
24 | Done | 2024-07-02 |  | 2024-10-03 |  | Finalize the Tax Report (108) & Update the Salary Tax Certificate | High | tecnical | Tawhid Sir | Amir Hamza | Mr.Haque
25 | Done | 2024-07-02 |  | 2024-07-10 |  | AIT & TDS macro syncronizing run time error issue when multipule entry in one batch | High | tecnical | Hamza bin Habibur | Amir Hamza | Mr.Haque
26 | Done | 2024-07-28 |  | 2024-08-04 |  | Receipt report ammount show in january that will be show in april | High | tecnical | Hamza bin Habibur | Amir Hamza | Mr.Haque
27 | Done | 2024-07-31 |  | 2024-08-11 |  | AR Receipt post error batch number 27028-Accpac issue | High | tecnical | Hamza bin Habibur | Amir Hamza | Mr.Haque
28 | Done | 2024-08-08 |  | 2024-08-20 |  | Credit receipt 29th july showed as a run time error during synchronizing-Accpac issue (Check mail in details) | High | tecnical | Hamza bin Habibur | Amir Hamza | Mr.Haque
29 | Done | 2024-08-11 |  | 2024-08-20 |  | Opening new ID in Accpac-Accpac issue (Check mail in details) | High | Tecnical | Amir Hamza | Amir Hamza | Mr.Haque
30 | Done | 2024-08-11 |  | 2024-08-12 |  | Norming Asset management Year End Process -Accpac issue (Check mail in details) | High | tecnical | Towhid sir | Amir Hamza | Mr.Haque
31 | Done | 2024-08-27 |  | 2024-08-28 |  | Biggan chinta (41-1012-99) increase iteam number as like kishore alo (41-1006-0133)-Accpac issue | High | Functional | Towhid sir | Amir Hamza | Mr.Haque
32 | Done | 2024-08-27 |  | 2024-08-28 |  | Audit (External audit) AM Disposal entry error (Batch number-092059)-Accpac issue | High | Functional | Towhid sir | Amir Hamza | Mr.Haque
33 | Done | 2024-09-03 |  | 2024-09-08 |  | Accpac Access to External Auditor-Accpac issue (Check mail in details) | High | Functional | Towhid sir | Amir Hamza | Mr.Haque
34 | Done | 2024-09-08 |  | 2024-09-08 |  | Accpac VAT macro Run time error | High | tecnical | Hamza bin Habibur | Amir Hamza | Mr.Haque
35 | Done | 2024-09-09 |  | 2024-09-09 |  | Accpac VAT macro (Corki) Run time error | High | tecnical | Hamza bin Habibur | Amir Hamza | Mr.Haque
36 | Done | 2024-09-09 |  | 2024-09-17 |  | Request for Access to Financial Statements Report in Accpac | High | Functional | Amir Hamza | Amir Hamza | Mr.Haque
37 | Done | 2024-09-25 |  | 2024-09-25 |  | Create GL Head in ACCPAC-TCPL issue | High | Functional | Towhid sir+Amir Hamza | Amir Hamza | Mr. Shoriful
38 | Done | 2024-09-25 |  | 2024-09-25 |  | Addition of new item in Accpac-TCPL issue | High | Functional | Towhid Sir+Amir Hamza | Amir Hamza | Mr. Bilal
39 | Done | 2024-09-30 |  | 2024-10-01 |  | Create GL Head in ACCPAC-TCPL issue | High | Functional | Towhid Sir+Amir Hamza | Amir Hamza | Mr.Shoriful
40 | Done | 2024-10-01 |  | 2024-10-02 |  | ABOM Sales statement 20 sep report mismatch with Accpac | High | Tecnical | Mamun | Amir Hamza | Mr.Haque
41 | Done | 2024-10-01 |  | 2024-10-15 |  | ABOM Receipt report ammount mismatch with Accpac | High | Tecnical | Tawhid sir+Ridwan | Amir Hamza | Mr.Haque
42 | Done | 2024-10-31 |  | 2024-11-03 |  | Incorporate New GL Head for Chorki in Accpac | High | Functional | Tawhid sir+Amir Hamza | Amir Hamza | Mr.Haque
Done

## PALO Application
Please enter the deadline for solving your allocation issue.
SL | Status | Date of Issue Raised | Date of Issue Solved | Date of Issue ReSolved | Issue | Priority | Solved By | Responsible Person | Issue Raised By- Business User | Remarks
2 | Done | 2024-02-06 |  |  | Check auto mail | High |  | Amir Hamza | Mr. Haque
3 | Done |  |  |  | ABOM user permission problem (user: fatema+mehedi cannot credit booking & rony cannot receive cash booking) | High | Mamun | Amir Hamza | Mr. Haque
4 | Done | 2023-12-13 | 2024-01-15 |  | ABOM user nazim motijhil to tikatuli (transfer) | High | Mamun | Amir Hamza | Mr. Haque
5 | Done | 2024-01-17 | 2024-01-31 |  | ABOM user nazim motijhil to tikatuli (transfer) update GL | High |  | Amir Hamza | Mr.Haque
6 | Done | 2023-12-14 |  |  | ABOM sales statement report and history amount mismatch (Jan-Dec) 2023 | High | Mamun | Amir Hamza | Mr. Haque
8 | Done | 2023-12-13 |  |  | Bill calculation finds wrong rana advertising- ABOM issue (Check mail in details) | High | Mamun | Amir Hamza | Mr. Haque
8 | Done | 2023-12-24 |  |  | Modification in ABOM category changes option to Apurba (Check mail in details) | High | Mamun | Amir Hamza | Mr. Haque
9 | Done | 2023-12-24 | 2024-01-29 |  | Update the contact person's name in Surjo- Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr. Firoz
10 | Done | 2023-12-31 |  |  | Vatable Amount showed blank on bill - ABOM issue (Check mail in details) | High | Mamun | Amir Hamza | Mr. Haque
11 | Done | 2024-01-04 | 2024-01-08 |  | VAT challan Receivable of Chorki couldn't find in the VAT report and Macro - ABOM issue (Check mail in details) | High | Mamun | Amir Hamza | Mr. Haque
12 | Done | 2024-01-11 | 2024-01-28 |  | Annex Communication some error in ABOM reversed ( Reversed Date 30.11.2023) - ABOM issue (Check mail in details) | High | Mamun | Amir Hamza | Mr. Haque
13 | Done | 2024-01-11 | 2024-01-22 |  | 23121033050 which is showing the wrong status - Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr. Firoz
14 | Done | 2024-01-11 | 2024-01-14 |  | IO23101032789 and send this to the integration stage - Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr. Firoz
15 | Done | 2024-01-11 | 2024-01-29 |  | social team couldn't find this IO-23121033029 in waiting for the adopts publication menu ber to publish- Surjo issue (Check mail in details) | High | Mamun | Amir Hamza | Mr. Firoz
16 | Done | 2024-01-11 | 2024-01-16 |  | Please check the following IO and send this IO to the integration stage. - Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr. Firoz
17 | Done | 2024-01-14 | 2024-01-16 |  | send back this IO-23011031624 to the integration - Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr. Firoz
17 | Done | 2024-01-16 | 2024-01-18 |  | IO-23111032903 status has not changed from waiting from adops publication to published.- Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr. Firoz
18 | Done | 2024-01-16 | 2024-01-22 |  | Customer contact email update in Surjo- Surjo issue (Check mail in details) | High | Mamun | Amir Hamza | Mr. Firoz
19 | Done | 2024-01-18 | 2024-01-18 |  | send back this IO-23121033040 to the integration stage.- Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr. Firoz
20 | Done | 2024-01-22 | 2024-01-28 |  | cancel this IO: 24011033155 & also delete from Surjo app.- Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr. Firoz
21 | Done | 2024-01-23 | 2024-01-24 |  | send back this IO-23111032903 to the integration - Surjo issue (Check whatsapp group in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
22 | Done | 2024-01-24 | 2024-01-29 |  | cancel this IO-24011033123 from Surjo- Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
23 | Done | 2024-01-25 | 2024-01-28 |  | send this IO-23121033040 from waiting from adops publication to the integration stage.- Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
24 | Done | 2024-01-25 | 2024-02-07 |  | IO-23121033060 amount missmatch- Surjo issue (Check whatsapp group in details) | High | Dip, Amir Hamza | Amir Hamza | Mr.Firoz
25 | Done | 2024-01-25 | 2024-02-11 |  | IO-24011033165 view error and sent to waiting client approve - Surjo issue (Check whatsapp group in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
26 | Done | 2024-01-28 | 2024-01-30 |  | cancel this IO-24011033091 in surjo- Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr. Firoz
27 | Done | 2024-01-29 | 2024-01-31 |  | Send these IO to ready the bill stage (23111032918,23111032946) - Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
28 | Done | 2024-01-31 | 2024-02-01 |  | Circulation Rate issue (10 to 12 tk) | High | Mamun | Amir Hamza | Mr.Haque
29 | Done | 2024-01-31 | 2024-02-04 |  | Send back to the integration stage (IO-231010547) - Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
30 | Done | 2024-01-31 | 2024-02-04 |  | Update customer VAT field (21110-1006) in Surjo-surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
31 | Done | 2024-02-05 | 2024-02-07 |  | Replace the social report of this IO-23121033066 from the back end- Surjo issue (Check mail in details) | High | Mamun | Amir Hamza | MrFiroz
32 | Done | 2024-02-05 | 2024-02-05 |  | Send back this IO-23101032721 to the integration stage- Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
33 | Done | 2024-02-05 | 2024-02-06 |  | Sales statement credit receipt value mismatch-Abom issue | High | Mamun | Amir Hamza | Mr.Aziz
34 | Done | 2024-02-08 | 2024-02-11 |  | Change the RPT-00180358 of Receipt date from 29.01.24 to 24.01.24-Abom issue (Check mail in details) | High | Mamun | Amir Hamza | Mr.Haque
35 | Done | 2024-02-08 | 2024-02-12 |  | Send back this IO-23111032890 to the integration stage- Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
36 | Done | 2024-02-08 | 2024-02-12 |  | send this IO-23121032986 to the integration stage. - Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
37 | Done | 2024-02-10 | 2024-02-13 |  | send this IO-24011033101 to the integration stage.- Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
38 | Done | 2024-02-10 | 2024-02-13 |  | send this IO-24011033128 to the integration stage.- Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
39 | Done | 2024-02-10 | 2024-02-13 |  | send this IO-24011033097 to the integration stage.- Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
40 | Done | 2024-02-10 | 2024-02-14 |  | send this IO-24011033134 to the integration stage.- Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
41 | Done | 2024-02-14 | 2024-02-18 |  | change email address of the contract person of this customer-21104-2744 -Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
42 | Done | 2024-02-19 | 2024-02-20 |  | send back this IO-23111032926 to the integration stage- Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
43 | Done | 2024-02-20 | 2024-02-22 | 2024-02-25 | send this IO-23061032292 to the integration stage - Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
44 | Done | 2024-02-22 | 2024-02-25 |  | send this IO-24011033159 to the integration stage - Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
45 | Done | 2024-02-27 | 2024-02-28 |  | update the address of this customer 21104-1676 in Surjo as per ACCPAC | High | Amir Hamza | Amir Hamza | Mr.Firoz
46 | Done | 2024-03-02 | 2024-03-06 |  | Update gross amount IO-24031033358 in surjo-(Check whatsapp group in details) | High | Dip, Amir Hamza | Amir Hamza | Mr.Firoz
47 | Done | 2024-03-02 | 2024-03-06 |  | Media Baying Editable issue-surjo issue | High | Dip, Amir Hamza | Amir Hamza | Mr.Firoz
48 | Done | 2024-03-03 | 2024-03-03 |  | Disable the user account from ABOM & ACCPAC as soon as possible-ABOM issue (Check mail in details) | High | Mamun+Jitu | Amir Hamza | Mr.Haque
49 | Done | 2024-03-03 | 2024-03-03 |  | Disable the user account from ABOM & ACCPAC as soon as possible-ABOM issue (Check mail in details) | High | Mamun+Jitu | Amir Hamza | Mr.Haque
50 | Done | 2024-03-03 | 2024-03-03 |  | Re-send passwod for ABOM-ABOM issue | High | Mamun | Amir Hamza | Mr.Haque
51 | Done | 2024-03-03 | 2024-03-04 |  | Change contact detail-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
52 | Done | 2024-03-04 | 2024-03-05 |  | Advertisement booking publish date change-ABOM issue (Check mail in details) | High | Mamun | Amir Hamza | Mr.Haque
53 | Done | 2024-03-05 | 2024-03-06 |  | Disable the user account from ABOM & ACCPAC as soon as possible-ABOM issue (Check mail in details) | High | Mamun | Amir Hamza | Mr.Haque
54 | Done | 2024-03-06 | 2024-03-07 |  | Update customer VAT field (21110-1006) in Surjo-surjo issue (Check mail in details) | High | Dip, Amir Hamza | Amir Hamza | Mr.Firoz
55 | Done | 2024-03-09 | 2024-03-10 |  | Work order cancellation required-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
56 | Done | 2024-03-09 | 2024-03-12 |  | send back this IO-23121033060 to the integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
57 | Done | 2024-03-09 | 2024-03-12 |  | send back this IO-24011033150 to the integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
58 | Done | 2024-03-09 | 2024-03-13 |  | send this IO-24011033202 to the integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
59 | Done | 2024-03-10 | 2024-03-10 |  | change this receipt mood and remit to bank mood Nagad from Bkash-ABOM issue (Check mail in details) | High | Mamun | Amir Hamza | Mr.Haque
60 | Done | 2024-03-12 | 2024-03-18 |  | send this IO-24011033101 to the integration stage.- Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
61 | Done | 2024-03-12 | 2024-03-18 |  | send back this IO-23121032980 to the integration stage.- Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
62 | Done | 2024-03-19 | 2024-03-21 |  | send this IO-24011033150 to the integration stage. | High | Amir Hamza | Amir Hamza | Mr.Firoz
63 | Done | 2024-03-24 | 2024-06-10 |  | Chattogram route changing issue-ABOM issue (Check mail in details) | High |  | Amir Hamza | Mr.Haque
64 | Done | 2024-03-24 | 2024-05-08 |  | IO-23121033060 value in Surjo does not match with ACCPAC value- Surjo issue (Check mail in details) | High | Mr.Firoz + Amir Hamza | Amir Hamza | Mr.Firoz
65 | Done | 2024-03-24 | 2024-04-15 |  | IO-24031033370 Marketing and DFP team couldn't find- Surjo issue (Check mail in details) | High | Mr.Firoz + Amir Hamza | Amir Hamza | Mr.Firoz
66 | Done | 2024-03-28 | 2024-05-13 |  | Year 2024 not show in NP_FestivalBonus_Email -ABOM issue | High | Afrin | Amir Hamza | Mr.Haque
67 | Done | 2024-03-29 | 2024-04-04 |  | BKN-00548705 some Rpt receipt and some Rpt cancel send cancel Rpt in normal position-ABOM issue | High | Ridwan | Amir Hamza | Mr.Haque
68 | Done | 2024-03-29 | 2024-04-02 |  | update the report of the following IO from the back end as per the attached file.-Surjo issue (Check mail in details) | High | Mr.Firoz + Amir Hamza | Amir Hamza | Mr. Firoz
69 | Done | 2024-04-02 | 2024-04-02 |  | REPLACE REPORT-AC MELA.-Surjo issue (Check mail in details) | High | Mr.Firoz + Amir Hamza | Amir Hamza | Mr.Firoz
70 | Done | 2024-04-02 | 2024-04-03 |  | Cancel this IO-2404101229 -Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
71 | Done | 2024-04-03 | 2024-04-03 |  | send these IO to the integration stage because of showing wrong status.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
72 | Done | 2024-04-03 | 2024-04-03 |  | send this IO-24031033366 to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
73 | Done | 2024-04-02 | 2024-04-04 |  | Send back this IO-23121032980 to integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
74 | Done | 2024-04-16 | 2024-04-17 |  | Replace the social report of this IO-24011033161 from the back end.-Surjo issue (Check mail in details) | High | Alif | Amir Hamza | Mr.Firoz
75 | Done | 2024-04-17 | 2024-05-06 |  | Prothoma prokashon Branch FR report profit and loss mismatch amount | High | Tawhid sir | Amir Hamza | Mr.Haque
76 | Done | 2024-04-18 | 2024-04-18 |  | Cancel this IO-24011033165 from Surjo-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
77 | Done | 2024-04-21 | 2024-04-24 |  | Update this customer-21104-2138 information in Surjo as per ACCPAC.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
78 | Done | 2024-04-22 | 2024-04-22 |  | IO-23111032926 to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
79 | Done | 2024-04-22 | 2024-04-22 |  | This IO-24031033428 not found social and DFP team in published folder -Check Whatsapp group in details | High | Mamun | Amir Hamza | Mr.Firoz
80 | Done | 2024-04-25 | 2024-04-25 |  | BKN-00581198 changed status Reversed to Confirm-ABOM issue | High | Ridwan | Amir Hamza | Mr.Haque
81 | Done | 2024-04-25 | 2024-04-28 |  | send back this IO-24031033354 to the integration stage -Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
82 | Done | 2024-04-25 |  |  | sales statement report classified not print properly-Abom issue | High |  | Amir Hamza | Mr.Haque
83 | Done | 2024-04-29 | 2024-04-29 |  | send this IO-24031033371 to the integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
84 | Done | 2024-04-29 | 2024-05-06 |  | send back this IO-24041033538 to the integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
85 | Done | 2024-04-29 | 2024-05-02 |  | update the IO as per the below-marked changes-Surjo issue (Check mail in details) | High | Dip+Mamun | Amir Hamza | Mr.Firoz
86 | Done | 2024-04-30 | 2024-05-02 |  | Amberkhana branch shylet salary FR report amount mismatch in PL | High | jitu | Amir Hamza | Mr.Haque
87 | Done | 2024-04-30 | 2024-05-02 |  | Abom cash syncronize 26 apr sales data show 10 lakh 54 thousand 797 tk when pass in accpac it show 10 lakh 56 thousand 637 tk | High | Mamun | Amir Hamza | Mr.Haque
88 | Done | 2024-04-30 | 2024-05-05 |  | kisshore alo syncronize error in circulation automation process then combine window for all micro | High | Afrin | Amir Hamza | Mr.Haque
89 | Done | 2024-04-30 | 2024-05-06 |  | send this IO-24031033354 to integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
90 | Done | 2024-05-04 | 2024-05-07 |  | send back this IO-24041033518 to the integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
91 | Done | 2024-05-05 | 2024-05-06 |  | New BKN-00581308 created in ABOM status show booking sycronize but data not pass in Accpac | High | Mamun | Amir Hamza | Mr.Haque
92 | Done | 2024-05-05 | 2024-05-06 |  | PRMS date: 04/05/2024 consumption report no 9219 ctg press issue | High | Ridwan | Amir Hamza | Mr.Haque
93 | Done | 2024-05-05 | 2024-05-09 |  | PRMS loan return file attach runtime error issue | High | Ridwan | Amir Hamza | Mr.Haque
94 | Done | 2024-05-06 | 2024-05-08 |  | send this IO-24041033537 to the integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
95 | Done | 2024-05-07 | 2024-05-08 |  | send this IO-24031033397 to the integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
96 | Done | 2024-05-07 | 2024-05-12 |  | send this IO-24031033443 to the integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
97 | Done | 2024-05-07 | 2024-05-12 |  | send this IO-24031033446 to the integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
98 | Done | 2024-05-07 | 2024-05-08 |  | send this IO-24031033397 to the integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
99 | Done | 2024-05-07 | 2024-05-13 |  | send this IO-23051032073 to the integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
100 | Done | 2024-05-07 | 2024-05-09 |  | send this IO-23121033050 to the published stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
101 | Done | 2024-05-08 | 2024-05-08 |  | send back this IO-24021033273 to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
102 | Done | 2024-05-09 | 2024-05-15 |  | update the DFP report of this IO- 24041033589 from the back end.-Surjo issue (Check mail in details) | High | Dip | Amir Hamza | Mr.Firoz
103 | Done | 2024-05-12 | 2024-05-14 |  | cancel this IO:24051033668-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
104 | Done | 2024-05-13 | 2024-05-19 |  | send back the following IO to the integration stage. .-Surjo issue (Check mail in details) | High | Mamun | Amir Hamza | Mr.Firoz
105 | Done | 2024-05-19 | 2024-05-19 |  | ABOM micro create with new path shortcut in userdesktop | High | Amir Hamza | Amir Hamza | Mr.Haque
106 | Done | 2024-05-19 | 2024-05-19 |  | Accpac sub mudule W/R transection tag with new path | High | Amir Hamza | Amir Hamza | Mr.Haque
107 | Done | 2024-05-19 | 2024-05-26 |  | Send Back the IO-23121033050 to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
108 | Done | 2024-05-19 | 2024-05-22 |  | Please update the following contact detail of the customer 21104-2710 in Surjo. | High | Amir Hamza | Amir Hamza | Mr.Firoz
109 | Done | 2024-05-20 | 2024-05-28 |  | Wrong quantity impression show.-Surjo issue (Check mail in details) | High | Firoz vai | Amir Hamza | Mr.Firoz
110 | Done | 2024-05-22 | 2024-05-27 |  | update the customer-21104-2044 in Surjo as per the following information. | High | Amir Hamza | Amir Hamza | Mr.Firoz
111 | Done | 2024-05-26 | 2024-05-27 |  | Biplob Advertising Bkn-00586396, Rpt No-00185196 update category | High | Amir Hamza | Amir Hamza | Mr.Haque
112 | Done | 2024-05-26 | 2024-06-02 |  | this IO- 24021033351. It's showing the wrong status. DFP and Social team already published this IO-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
113 | Done | 2024-05-27 | 2024-05-28 |  | Rpt.00185179, BKN-00586476 is reveived By Bkash Mode by mistake.But it will be Nagad Mode.-Abom issue (Check mail in details) | High | Mamun | Amir Hamza | Mr.Haque
114 | Done | 2024-05-27 | 2024-06-06 |  | create the following users in Circulation Module as soon as possible.-circulation issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Haque
115 | Done | 2024-05-28 | 2024-06-10 |  | change the contact details of this customer 21104-2648 in Surjo as per the information-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
116 | Done | 2024-05-30 | 2024-06-03 |  | Kisshore alo and biggan chinta shipment error automation process then combine window for all micro | High | Ridwan | Amir Hamza | Mr.Haque
117 | Done | 2024-06-01 | 2024-06-06 |  | check this IO-24051033751 showing double-Surjo issue (Check whatsapp in details) | High | Mamun | Amir Hamza | Mr.Firoz
118 | Done | 2024-06-01 | 2024-07-14 |  | New Challan 2 exe report bornil boshot,and bissho kaper chokka not showing | High | Abul Haque | Amir Hamza | Mr.Sabu, Belayet
119 | Done | 2024-06-02 | 2024-06-10 |  | send this IO-24041033538 to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
120 | Done | 2024-06-03 | 2024-06-13 |  | update the DFP report of this IO-24031033413 from the back end.-Surjo issue (Check mail in details) | High | Dip | Amir Hamza | Mr.Firoz
121 | Done | 2024-06-05 | 2024-06-23 |  | order basis sales analysis report show 10 quantity extra from 1 may to 31 may | High | Mamun | Amir Hamza | Mr.Haque
122 | Done | 2024-06-09 | 2024-06-12 |  | paribahan name change in biggan chinta-press issue | High | Mamun | Amir Hamza | Mr.Haque
123 | Done | 2024-06-05 | 2024-06-06 |  | combine window for all micro OE shipment from 1 may-31 may run time error | High | Ridwan | Amir Hamza | Mr.Haque
124 | Done | 2024-06-05 | 2024-06-06 |  | circulation synopsis report can not show all vendor from 1 may-31 may | High | Ridwan | Amir Hamza | Mr.Haque
125 | Done | 2024-06-05 | 2024-06-06 |  | send back this IO-24051033649 to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
126 | Done | 2024-06-06 | 2024-06-06 |  | send back those 6 IO to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
127 | Done | 2024-06-06 | 2024-06-13 |  | update the contact name of this customer-21104-2802. Name will be Zobaer Ahmed.-Surjo issue(Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
128 | Done | 2024-06-11 | 2024-06-23 |  | send back this IO-24051033672 to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
129 | Done | 2024-06-12 | 2024-06-27 |  | send back this IO-24011033151 to the integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
130 | Done | 2024-06-26 | 2024-07-02 |  | send back this IO-24051033719 to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
131 | Done | 2024-06-27 | 2024-07-02 |  | send back this IO-24051033657 to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
132 | Done | 2024-06-27 | 2024-07-03 |  | cancel these IO- 24061033889 & 24061033880 from Surjo.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
133 | Done | 2024-07-01 | 2024-07-07 |  | send this IO-24051033747 to the published stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
134 | Pending | 2024-07-01 | 2024-08-29 |  | New Location Open and core transfer from ctg to dhk in the PRMS-(Check mail in details) | High | Afrin+Ridwan | Amir Hamza | Mr.Haque
135 | Done | 2024-07-01 | 2024-07-07 |  | Combine window for all micro OE shipment ammount missmatch | High | Ridwan | Amir Hamza | Mr.Haque
136 | Done | 2024-07-02 | 2024-07-08 |  | Send this IO-24051033726 to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
137 | Done | 2024-07-03 | 2024-07-08 |  | Send this IO-24061033803 to published stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
138 | Done | 2024-07-07 | 2024-07-09 |  | Replace the social report of this IO-24051033709 in Surjo.-Surjo issue (Check mail in details) | High | Dip | Amir Hamza | Mr.Firoz
139 | Done | 2024-07-08 | 2024-07-11 |  | Add this DFP report and send this IO to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
140 | Done | 2024-07-11 | 2024-07-16 |  | IO-(24071033978,24071033971) from your end. VAT amount not calculated. Accpac Customer ID (21104-2810,21104-2808)-Surjo issue (Check mail in details) | High | Amir Hamza+Mamun | Amir Hamza | Mr.Firoz
141 | Done | 2024-07-28 | 2024-07-28 |  | IO Account for Mahmud Hasan-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
142 | Done | 2024-07-26 | 2024-08-29 |  | CTG Core/Role transfer PALO Production Floor CTG to Prothom Alo Godown-DHK | High | Afrin | Amir Hamza | Mr.Haque
143 | Done | 2024-07-27 | 2024-07-31 |  | IO Account for Mahmud Hasan-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
144 | Done | 2024-07-30 | 2024-08-04 |  | Please send back these IO to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
145 | Done | 2024-07-31 | 2024-08-04 |  | Replace the updated social report from the back end.-Surjo issue (Check mail in details) | High | Dip | Amir Hamza | Mr.Firoz
146 | Done | 2024-08-04 | 2024-08-07 |  | update the DFP report of this IO-24071033944 from the back end-Surjo issue (Check mail in details) | High | Dip | Amir Hamza | Mr.Firoz
147 | Done | 2024-08-07 | 2024-08-11 |  | replace the social report of this IO-24071033969 from the back end-Surjo issue (Check mail in details) | High | Dip | Amir Hamza | Mr.Firoz
148 | Done | 2024-08-07 | 2024-08-11 |  | send this IO-24061033864 to the integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
149 | Done | 2024-08-08 | 2024-08-11 |  | send this IO-24051033747 to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
150 | Done | 2024-08-08 | 2024-08-21 |  | send this IO-24061033798 to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
151 | Done | 2024-08-13 | 2024-08-22 |  | send this IO-24071033997 to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
152 | Done | 2024-08-20 | 2024-08-27 |  | New brand name - Resolute - USA-PRMS issue (Check mail in details) | High | Ridwan | Amir Hamza | Mr.Manik
153 | Done | 2024-08-25 | 2024-09-02 |  | send this IO-24071033997 to the integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
154 | Done | 2024-08-26 | 2024-09-11 |  | Report 24081034115 not download from surjo | High | Dip | Amir Hamza | Mr.Firoz
155 | Done | 2024-08-28 | 2024-09-02 |  | RPT-00188593 Status change from Posted' to 'Entered' | High | Mr.Haque | Amir Hamza | Mr.Haque
156 | Done | 2024-09-01 | 2024-09-12 |  | Advance-00000341 not show in receipt page | High | Ridwan | Amir Hamza | Mr.Haque
157 | Done | 2024-09-02 | 2024-09-03 |  | Circulation newspaper copy error delete those copy | High | Database Connection Issue | Amir Hamza | Mr.Haque
158 | Done | 2024-09-02 | 2024-09-09 |  | PRMS Inventory status Location 400110 report preview Error | High | Afrin | Amir Hamza | Mr.Harun
159 | Done | 2024-09-02 | 2024-09-18 |  | NP Tax Report issue-Palo issue | High | Mamun | Amir Hamza | Mr. Haque
160 | Done | 2024-09-02 | 2024-09-03 |  | A/R invoice batch post show error | High | Database Connection Issue | Amir Hamza | Mr.Haque
161 | Done | 2024-09-02 | 2024-09-04 |  | ABOM BKN ('BKN-00595688','BKN-00595689','BKN-00595690') Status Change Reverse to Confirm Stage-ABOM issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Haque
162 | Done | 2024-09-02 | 2024-09-05 |  | RPT-00188846 & RPT-00188847 of Receipt date from 29.08.24 to 28.08.24 | High | Amir Hamza | Amir Hamza | Mr.Haque
163 | Done | 2024-09-03 | 2024-09-05 |  | IO-24081034044 from your end. The report attachment option is missing.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
164 | Done | 2024-09-03 | 2024-09-09 |  | send back these IO 24041033635 and 24031033442 to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
165 | Done | 2024-09-03 | 2024-09-04 |  | 30 Aug er credit note wrong status show in report-ABOM issue (Check mail in details) | High | Mamun | Amir Hamza | Mr.Haque
166 | Done | 2024-09-03 | 2024-09-08 |  | send back this IO-23091032669 to the integration stage and cancel the IO.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
167 | Done | 2024-09-04 | 2024-09-09 |  | New Brand add in PRMS system Name: Hylte - Sweden -PRMS issue (Check mail in details) | High | Ridwan+Amir Hamza | Amir Hamza | Mr.Manik
168 | Done | 2024-09-04 | 2024-09-09 |  | New Brand add in PRMS system Name: Norske Shog - Norway -PRMS issue (Check mail in details) | High | Ridwan+Amir Hamza | Amir Hamza | Mr.Manik
169 | Done | 2024-09-09 | 2024-10-01 |  | Consumption Related Report: reort type-reel handover 400110 to 400130 (to location data not found)-PRMS issue | High | Afrin | Amir Hamza | Mr.Amzad
170 | Done | 2024-09-09 | 2024-09-17 |  | Receipt,Loan,transfer, New location Chanan number not found | High | Afrin | Amir Hamza | Mr.Amzad
171 | Done | 2024-09-08 | 2024-09-10 |  | In reel distribuition system-Kachpur production floor and Kachpur godown not found-PRMS issue | High | Afrin | Amir Hamza | Mr.Manik
172 | Done | 2024-09-10 | 2024-09-12 |  | VAT calculation Issue-Surjo issue (Check mail in details) | High | Dip | Amir Hamza | Mr.Firoz
173 | Done | 2024-09-11 | 2024-09-17 |  | Please send back the following IO to the integration stage.-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
174 | Done | 2024-09-12 | 2024-09-12 |  | Send IO-24091034201 Adops publication to published stage | High | Amir Hamza | Amir Hamza | Mr.Firoz
178 | Done | 2024-09-17 | 2024-09-23 |  | Send Back this IO-24051033686 to integration stage-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
179 | Done | 2024-09-18 | 2024-09-24 |  | Time card entry issue-Palo issue | High | Tawhid sir | Amir Hamza | Mr.Haque
180 | Pending | 2024-09-22 |  |  | Circulation autometion process combine window for all micro (OE return report 1aug-31aug)-Palo issue | High | Ridwan | Amir Hamza | Mr.Haque
181 | Done | 2024-09-23 | 2024-09-26 |  | send this IO-24091034201 to the published stage because the social file is missing. | High | Amir Hamza | Amir Hamza | Mr.Firoz
182 | Done | 2024-09-24 | 2024-09-25 |  | File not upload in reel distribuition-Palo issue | High | Afrin | Amir Hamza | Mr.Manik
183 | Done | 2024-09-29 | 2024-09-02 |  | Cancel this IO-24091034298 in Surjo-Surjo issue (Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
184 | Done | 2024-09-29 | 2024-10-01 |  | 10 to 12 tk for daily newspaper-Circulation issue | High | Mamun | Amir Hamza | Mr.Haque
185 | Pending | 2024-09-29 |  |  | Auto mail not working-ABOM issue | High | Ridwan | Amir Hamza | Mr.Haque
186 | Done | 2024-10-06 | 2024-10-08 |  | Please change the social report of this IO-24091034180 from the back end.-Surjo issue(Check mail in details) | High | Dip | Amir Hamza | Mr.Firoz
187 | Done | 2024-10-07 | 2024-10-07 |  | Please send back this IO-24081034096 to the integration stage.-Surjo issue(Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
188 | Done | 2024-10-07 | 2024-10-16 |  | Send back this IO-24091034221 to the integration stage-Surjo issue(Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
189 | Done | 2024-10-17 | 2024-10-21 |  | Send this IO-24091034249 to the published stage-Surjo issue(Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
190 | Done | 2024-10-20 | 2024-10-21 |  | send this IO-24061033908 to the published stage-Surjo issue(Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
191 | Done | 2024-10-21 | 2024-10-22 |  | send this IO-24051033686 to the integration stage-Surjo issue(Check mail in details) | High | Amir Hamza | Amir Hamza | Mr.Firoz
192 | Done | 2024-10-22 | 2024-10-22 |  | Transection confirm status report show some published BKN-ABOM issue | High | Mamun | Amir Hamza | Mr.Haque
193 | Pending | 2024-10-22 |  |  | Credit booking RPT get rony vai before invoice-ABOM issue | High |  | Amir Hamza | Mr.Haque
194 | Done | 2024-10-23 | 2024-10-27 |  | DBL Ceramics Report Replace - 24091034237-Surjo issue | High | Dip+Amir Hamza | Amir Hamza | Mr.Firoz
195 | Done | 2024-10-27 | 2024-10-27 |  | Abashon Mela SARE Report Replace - 24091034273-Surjo issue | High | Dip+Amir Hamza | Amir Hamza | Mr.Firoz
196 | Done | 2024-10-28 | 2024-10-28 |  | send back this IO-24101034371 to the integration stage-Surjo issue | High | Amir Hamza | Amir Hamza | Mr.Firoz
197 | Done | 2024-10-29 | 2024-10-29 |  | Send Back this IO-24031033428 to the integration stage-Surjo issue | High | Amir Hamza | Amir Hamza | Mr.Firoz
198 | Done | 2024-10-31 | 2024-11-04 |  | Adjustment Request for cancel IO- 24081034155 – Kohinoor Chemicals Ltd-surjo issue | High | Amir Hamza | Amir Hamza | Mr.Firoz
199 | Done | 2024-11-05 | 2024-11-06 |  | Send back to the integration stage IO-24091034264, 24091034214-surjo issue | High | Amir Hamza | Amir Hamza | Mr.Firoz
200 | Done | 2024-11-05 | 2024-11-07 |  | PO replace the client approval file of this IO- 24091034191 from the back end.-Surjo issue | High | Amir Hamza | Amir Hamza | Mr.Firoz
201 | Done | 2024-11-05 | 2024-11-07 |  | Request to replace the attached report 24091034291-Surjo issue | High | Amir Hamza | Amir Hamza | Mr.Firoz
202 | Done | 2024-11-06 | 2024-11-07 |  | Sent the IO-24091034249 to integration stage-Surjo issue | High | Amir Hamza | Amir Hamza | Mr.Firoz
203 | Done | 2024-11-06 | 2024-11-10 |  | send this IO-24081034164 to the integration stage.-Surjo issue | High | Amir Hamza | Amir Hamza | Mr.Firoz
204 | Done | 2024-11-07 | 2024-11-14 |  | replace the DFP report of this IO-24091034319 from the back end as per attached file..-Surjo issue | High | Amir Hamza | Amir Hamza | Mr.Firoz
205 | Done | 2024-11-07 | 2024-11-14 |  | replace the DFP report of this IO 24091034317 from the back end..-Surjo issue | High | Amir Hamza | Amir Hamza | Mr.Firoz
206 | Pending | 2024-11-07 |  |  | Please send this IO-24091034290 to integration stage. | High | Amir Hamza | Amir Hamza | Mr.Firoz
207 | Done | 2024-11-10 | 2024-11-10 |  | Send back this IO-24091034219 to integration stage | High | Amir Hamza | Amir Hamza | Mr.Firoz

## Additional Support With Date &
SL | Status | Date of Daily Work | Issue | Priority | Solved By | Responsible Person | Time
1 | Done | 2024-09-17 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 09.45-10.30
2 | Done | 2024-09-17 | Send Back this IO-24051033686 to integration stage-PALO issue | High | Amir Hamza | Amir Hamza | 10.30-11.00
2 | Done | 2024-09-17 | Commuinicate smart vendor rony about TCPL report-TCPL issue | High | Amir Hamza | Amir Hamza | 4.00-5.30
3 | Done | 2024-09-18 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 09.45-10.30
4 | Done | 2024-09-18 | Taking All Corporate Application and Database Backup-TCL issue | High | Amir Hamza | Amir Hamza | 11.00-12.30
5 | Done | 2024-09-18 | NP Tax Report issue-PALO issue | High | Mamun+Amir Hamza | Amir Hamza | 2.30-6.00
6 | Done | 2024-09-19 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
7 | Done | 2024-09-19 | Commuinicate with forhad vai check TFL server and increase drive space-TFL issue | High | Forhad vai | Amir Hamza | 10.30-11.00
8 | Done | 2024-09-19 | Commuinicate with dip vai and Shamsul alam about meet issue-TDCL issue | High | Amir Hamza | Amir Hamza | 11.30-12.00
9 | Done | 2024-09-19 | NP time card issue-PALO issue | High | Towhid sir | Amir Hamza | 2.30-6.00
10 | Done | 2024-09-22 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 09.45-10.30
11 | Resolved | 2024-09-22 | NP time card issue-PALO issue | High | Towhid sir | Amir Hamza | 11.00-6.00
12 | Done | 2024-09-23 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 11.30-12.00
13 | Done | 2024-09-23 | NP Tax Report date and alignment update-PALO issue | High | Amir Hamza | Amir Hamza | 12.00-1.30
14 | Done | 2024-09-23 | Salary sheet process-TCL isssue | High | Dip+Amir Hamza | Amir Hamza | 2.30-3.00
15 | Done | 2024-09-23 | Surjo stage change-PALO issue | High | Amir Hamza | Amir Hamza | 3.00-600
16 | Done | 2024-09-24 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 11.30-12.00
17 | Done | 2024-09-24 | GAL employee data upload in mytranscom-TCL isssue | High | Tamim | Amir Hamza | 3.00-600
18 | Done | 2024-09-24 | Commuinicate with smart erp for develop required report-TCPL issue | High | Rony | Amir Hamza | 3.00-5.30
19 | Done | 2024-09-25 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
20 | Done | 2024-09-25 | Taking All Corporate Application and Database Backup-TCL issue | High | Amir Hamza | Amir Hamza | 10.30-12.00
21 | Done | 2024-09-25 | File not upload in reel distribuition-Palo issue | High | Afrin Apu | Amir Hamza | 2.30-6.00
22 | Done | 2024-09-26 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 09.45-10.30
23 | Done | 2024-09-26 | Stage change in surjo-PALO issue | High | Amir Hamza | Amir Hamza | 10.30-11.00
24 | working | 2024-09-26 | OE Report ammount missmatch | High | Ridwan+Amir hamza | Amir Hamza | 2.00-4.30
25 | Done | 2024-09-26 | Create new item in Accpac-TCPL issue | High | Amir Hamza | Amir Hamza | 4.30-5.00
26 | Done | 2024-09-26 | Create new GL head in Accpac-TCPL issue | High | Tawhid sir+Amir Hamza | Amir Hamza | 5.30-6.00
27 | Done | 2024-09-30 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 09.45-10.30
28 | Done | 2024-09-30 | Consumption Related Report: reort type-reel handover 400110 to 400130 (to location data not found)-PALO issue | High | Afrin+Amir Hamza | Amir Hamza | 10.30-1.00
29 | Done | 2024-09-30 | Commuinicate with smart erp vendor for upload employee in the smart attendence system-TCPL issue | High | Rony-Vendor | Amir Hamza | 2.30-3.30
30 | Done | 2024-09-30 | OKR TBL data update in mytranscom communication-TCL | High | Tamim+Amir Hamza | Amir Hamza | 4.00-6.00
31 | Done | 2024-10-01 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 09.45-10.30
32 | Done | 2024-10-01 | Consumption Related Report: reort type-reel handover 400110 to 400130 (to location data not found)-PALO issue | High | Afrin | Amir Hamza | 10.30-1.00
33 | Done | 2024-10-01 | 10 to 12 tk for daily newspaper-PALO issue | High | Mamun | Amir Hamza | 11.00-12.00 | 1 hour
34 | working | 2024-10-01 | Circulation autometion process combine window for all micro (OE return report show 160)-Palo issue | High | Ridwan+Amir hamza | Amir Hamza | 2.30-4.30
35 | Done | 2024-10-01 | Surjo stage change-PALO issue | High | Amir Hamza | Amir Hamza | 4.30-5.15
36 | Done | 2024-10-01 | Create new GL head in Accpac-TCPL issue | High | Amir Hamza | Amir Hamza | 5.30-6.00
37 | Done | 2024-10-02 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 09.45-10.30
38 | Done | 2024-10-02 | Taking All Corporate Application and Database Backup-TCL issue | High | Amir Hamza | Amir Hamza | 10.30-12.30
39 | Done | 2024-10-02 | Disscus and show exiting issue with ridwan vai-PALO issue | High | Amir Hamza | Amir Hamza | 2.30-3.30
40 | Done | 2024-10-02 | ABOM Sales statement 20 sep report mismatch with Accpac-PALO issue | High | Mamun+Amir Hamza | Amir Hamza | 3.30-4.00 | 30 Min
41 | Done | 2024-10-02 | Cancel this IO in Surjo-PALO issue | High | Amir Hamza | Amir Hamza | 4.00-4.30
42 | Done | 2024-10-02 | Commuinicate with rony and tawhid sir about report- TCPL issue | High | Amir Hamza | Amir Hamza | 4.30-6.00
43 | Done | 2024-10-03 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 09.45-10.30
44 | Done | 2024-10-03 | TBL:OKR data migration & Launch of my transcom OKR | High | Tamim+Amir Hamza | Amir Hamza | 10.30-1.30
45 | Done | 2024-10-03 | Finalize the Tax Report (108) & Update the Salary Tax Certificate-PALO issue | High | Tawhid Sir+ Amir Hamza | Amir Hamza | 2.30- 4.00
46 | Done | 2024-10-03 | Commuinicate with PALO accounts and IT about auto mail-PALO issue | High | Amir Hamza+ PALO IT | Amir Hamza | 4.00-600
47 | Done | 2024-10-06 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 09.45-10.30
48 | Done | 2024-10-06 | Commuinicate with PALO IT about auto mail and provide pending issue list | High | Amir Hamza | Amir Hamza | 10.30-12.30
49 | Done | 2024-10-06 | TCPL user creation in server- TCPL issue | High | Atunu vai | Amir Hamza | 12.30-1.00
50 | Done | 2024-10-06 | TCPL PAYROLL user creation in system- TCPL issue | High | Tawhid Sir+ Amir Hamza | Amir Hamza | 2.00-3.00
51 | Done | 2024-10-06 | Commuinicate with Shafikul and Rony about TCPL report- TCPL issue | High | Amir Hamza+Shafikul+ Rony | Amir Hamza | 3.00-4.00
52 | Done | 2024-10-06 | ABOM Receipt report ammount mismatch with Accpac- PALO issue | High | Tawhid Sir+ Ridawn+ Amir Hamza | Amir Hamza | 4.00-6.00
53 | Done | 2024-10-07 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 09.45-10.30
54 | Done | 2024-10-07 | Send back to integration stage-PALO issue | High | Amir Hamza | Amir Hamza | 10.30-11.00
55 | Done | 2024-10-07 | Singapore training outstaion entry-TCL issue | High | Amir Hamza | Amir Hamza | 11.00-1.00
56 | Done | 2024-10-07 | commuinicate and training with Smart vendor and TCPL about new join data upload and overtime | High | Amir Hamza | Amir Hamza | 3.00-6.00
57 | Done | 2024-10-08 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 09.45-10.30
58 | Done | 2024-10-08 | Doth Barth leave balance update in mystranscom-TCL issue | High | Dip+Amir Hamza | Amir Hamza | 10.30-1.00
59 | Done | 2024-10-08 | Please change the social report of this IO-24091034180 from the back end.-Surjo issue(Check mail in details) | High | Dip+Amir Hamza | Amir Hamza | 2.30-3.00
60 | Done | 2024-10-08 | Singapore training outstaion entry-TCL issue | High | Amir Hamza | Amir Hamza | 3.00-6.00
61 | Done | 2024-10-09 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 09.45-10.30
62 | Done | 2024-10-09 | Taking All Corporate Application and Database Backup-TCL issue | High | Amir Hamza | Amir Hamza | 10.30-12.30
63 | Done | 2024-10-09 | Send back to integration stage-PALO issue | High | Amir Hamza | Amir Hamza | 12.30-1.00
64 | Done | 2024-10-14 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 09.45-10.30
65 | working | 2024-10-14 | Report OT time not showing uploaded employee name not show in job card-TCPL issue | High | Rony | Amir Hamza | 10.30-11.30
66 | Done | 2024-10-14 | Server connection and payroll system connection in user desktop | High | Amir Hamza | Amir Hamza | 11.30-1.00
67 | Done | 2024-10-14 | FG new iteam add in Accpac Traning with TCPL team-TCPL issue | High | Amir Hamza | Amir Hamza | 3.00-6.00
68 | Done | 2024-10-15 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 09.45-10.30
69 | Done | 2024-10-15 | Location deatils file preparing and uploading training-TCPL issue | High | Amir Hamza | Amir Hamza | 10.30-12.00
70 | Done | 2024-10-15 | ABOM Receipt report ammount mismatch with Accpac- PALO issue | High | Tawhid sir+Ridwan+Amir Hamza | Amir Hamza | 12.00-1.00
71 | Done | 2024-10-15 | New depo opening process training-TCPL issue | High | Tawhid+Amir Hamza | Amir Hamza | 2.30-6.00
72 | Done | 2024-10-16 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
73 | Done | 2024-10-16 | Taking All Corporate Application and Database Backup-TCL issue | High | Amir Hamza | Amir Hamza | 10.30-12.00
74 | Done | 2024-10-16 | Surjo stage change-PALO issue | High | Amir Hamza | Amir Hamza | 12.00-1.00
75 | Done | 2024-10-16 | Making document about FG item and new depo opening-TCPL issue | High | Amir Hamza | Amir Hamza | 2.30-6.00
76 | Done | 2024-10-17 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
77 | Done | 2024-10-17 | Show employee infromation data report download to HR-TCPL issue | High | Amir Hamza | Amir Hamza | 10.30-1.00
78 | Done | 2024-10-17 | Xcel sheet employee format setup to HR-TCPL issue | High | Dip+Amir Hamza | Amir Hamza | 2.00-3.00
79 | Done | 2024-10-17 | Press user face remote login problem in PRMS-PALO issue | High | Amir Hamza+Palo IT | Amir Hamza | 3.00-600
81 | Done | 2024-10-20 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
82 | Done | 2024-10-20 | Report OT time not showing monthly attendence and Job card-TCPL issue | High | Rony | Amir Hamza | 10.30-4.00
83 | Done | 2024-10-20 | User Create of Payroll Software-TDCL issue | High | Tawhid sir+Amir Hamza | Amir Hamza | 4.00-5.00
84 | Done | 2024-10-20 | Pricing setup & New Depot ID & Name ,Opening Access in Accpac Necessary Module-TCPL issue | High | Tawhid sir+Amir Hamza | Amir Hamza | 5.00-6.00
85 | Done | 2024-10-21 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
86 | Done | 2024-10-21 | Hodilay add in mytranscom and show HR-TDCL issue | High | Amir Hamza | Amir Hamza | 10.30-11.00
87 | Done | 2024-10-21 | Salary sheet process-TCL isssue | High | Tamim+Amir Hamza | Amir Hamza | 11.00-1.00
88 | Done | 2024-10-21 | Surjo stage change-PALO issue | High | Amir Hamza | Amir Hamza | 2.00-3.00
89 | Done | 2024-10-21 | Surjo stage change-PALO issue | High | Amir Hamza | Amir Hamza | 3.00-4.00
90 | Done | 2024-10-21 | Communicate with vendor and tcpl HR about shifting and add leave -TCPL issue | High | Tawhid sir+Amir Hamza | Amir Hamza | 4.00-6.00
91 | Done | 2024-10-22 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
92 | Done | 2024-10-22 | Commuinicate Skf HR about transfer employees show absent holiday (tongi plant) in mytranscom-TCL issue | High | Tamim+Amir Hamza | Amir Hamza | 10.30-12.00
93 | Done | 2024-10-22 | Transection confirm status report show published BKN-PALO issue | High | Mamun | Amir Hamza | 12.00-12.45 | 45 Min
94 | Done | 2024-10-22 | Gress time apply for corporate in mystranscom-TCL issue | High | Amir Hamza | Amir Hamza | 12.00-1.00
95 | Done | 2024-10-22 | Salary sheet process updated-TCL isssue | High | Tamim+Amir Hamza | Amir Hamza | 2.00-5.00
96 | Done | 2024-10-22 | Surjo stage change-PALO issue | High | Amir Hamza | Amir Hamza | 5.00-6.00
97 | Done | 2024-10-27 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
98 | Done | 2024-10-27 | Request to create new user ID in Accpac-TCPL issue | High | Amir Hamza | Amir Hamza | 10.30-12.00
99 | Done | 2024-10-27 | Doth Barth employee outsation checkin not show in mytranscom app-Doth Birth issue | High | Amir Hamza | Amir Hamza | 12.00-12.30
100 | Done | 2024-10-27 | Mytranscom OKR session expire error-SKF issue | High | Amir Hamza | Amir Hamza | 12.30-1.00
101 | Done | 2024-10-27 | Abashon Mela SARE Report Replace - 24091034273 | High | Dip+Amir Hamza | Amir Hamza | 2.00-2.30
102 | Done | 2024-10-27 | DBL Ceramics Report Replace - 24091034237-Surjo issue | High | Dip+Amir Hamza | Amir Hamza | 2.30-3.00
103 | Done | 2024-10-27 | Weekend not showing affter declare in mytranscom-TCL | High | Tamim+Amir Hamza | Amir Hamza | 3.00-6.00
104 | Done | 2024-10-28 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
105 | Done | 2024-10-28 | Replace file not find social team-PALO issue | High | Dip+Amir Hamza | Amir Hamza | 10.30-11.30
106 | Done | 2024-10-28 | Commuinicate with smart vendor about leave report-TCPL issue | High | Amir Hamza | Amir Hamza | 11.30-12.00
107 | Done | 2024-10-28 | Commuinicate with new user about server access and accpac login issue-TCPL issue | High | Amir Hamza | Amir Hamza | 12.00-1.00
108 | Done | 2024-10-28 | Surjo stage change-PALO issue | High | Amir Hamza | Amir Hamza | 2.00-3.00
109 | Done | 2024-10-28 | Marternity leave issue in MyTranscom-SKF issue | High | Amir Hamza | Amir Hamza | 3.00-6.00
110 | Done | 2024-10-29 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
111 | Done | 2024-10-29 | Commuinicate with smart vendor about leave report training-TCPL issue | High | Amir Hamza | Amir Hamza | 10.30-11.00
112 | Done | 2024-10-29 | Check auto mail issue-PALO issue | High | Amir Hamza | Amir Hamza | 11,00-1.00
113 | Done | 2024-10-29 | Commuinicate with Skf HR about manual attendence in mytranscom-SKF issue | High | Tamim+Amir Hamza | Amir Hamza | 2.00-3.00
114 | Done | 2024-10-29 | Disscus with Tawhid sir about TDCL user apply leave problem in mytranscom-TDCL issue | High | Tamim+Amir Hamza | Amir Hamza | 3.00-4.00
115 | Done | 2024-10-29 | Commuinicate with firoz vai and fix meeting about chorki balance sheet-PALO issue | High | Amir Hamza | Amir Hamza | 4.00-5.00
116 | Done | 2024-10-29 | Surjo stage change-PALO issue | High | Amir Hamza | Amir Hamza | 5.00-6.00
117 | Done | 2024-10-30 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
118 | Done | 2024-10-30 | Taking All Corporate Application and Database Backup-TCL issue | High | Amir Hamza | Amir Hamza | 10.30-12.00
119 | Done | 2024-10-30 | Update of Grade for MyTranscom-TDCL isuue | High | Tamim+Amir Hamza | Amir Hamza | 12.00-1.00
120 | Done | 2024-10-30 | Disscus about chorki balance sheet with tawhid sir -PALO issue | High | Tawhid sir+ Amir Hamza | Amir Hamza | 2.00-3.00
121 | Done | 2024-10-30 | Disscus with Tawhid sir about shift and OT report-TCPL issue | High | Tawhid sir+ Amir Hamza | Amir Hamza | 3.00-4.00
122 | Done | 2024-10-30 | disscus with hanif vai and farhad vai about database backup issue-TFL issue | High | Hanif+Farhad+Amir Hamza | Amir Hamza | 4.00-6.00
123 | Done | 2024-10-31 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
124 | Done | 2024-10-31 | Meeting with smart vendor about plant leave report-TCPL issue | High | Tawhid Sir+Shafikul+Amir Hamza | Amir Hamza | 10.30-1.00
125 | Done | 2024-10-31 | Meeting with Firoz vai about chorki balance sheet-PALO issue | High | Tawhid sir+Firoz+Amir Hamza | Amir Hamza | 2.00-4.00
126 | Done | 2024-10-31 | Create accpac Chorki GL head and include all segment | High | Tawhid sir+Amir Hamza | Amir Hamza | 4,00-6.00
127 | Done | 2024-11-03 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
128 | Done | 2024-11-03 | Create accpac Chorki GL head and include all segment (Resolved) | High | Amir Hamza | Amir Hamza | 10.30-11.30
129 | Done | 2024-11-03 | Meeting with Firoz vai about vendor transaction report-PALO issue | High | Tawhid Sir+Amir Hamza | Amir Hamza | 11.30-1.00
130 | Done | 2024-11-03 | mytranscom manullary entry show absent after approve by supervisor-SKF issue | High | Amir Hamza+Tamim | Amir Hamza | 2.00-3.00
131 | Done | 2024-11-03 | Item location code issue in Accpac-TCPL issue | High | Tawhid sir+Amir Hamza | Amir Hamza | 3.00-6.00
132 | Done | 2024-11-04 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
133 | Done | 2024-11-04 | Cancel IO in Surjo-PALO issue | High | Amir Hamza | Amir Hamza | 10.30-11.30
134 | Done | 2024-11-04 | mytranscom manullary entry not show type in Analtics attendence list-SKF issue | High | Tamim+Amir Hamza | Amir Hamza | 11.30-1.00
135 | Done | 2024-11-04 | commuinicate with plant HR and vendor about new employee attendence not show in the report-TCPL issue | High | Amir Hamza+Shafikul+ Rony | Amir Hamza | 2.00-3.00
136 | Done | 2024-11-04 | mytranscom OKR not visible-SKF issue | High | Tamim+Amir Hamza | Amir Hamza | 3.00-6.00
137 | Done | 2024-11-05 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
138 | Done | 2024-11-05 | Create new user in Accpac and given access-TCPL issue | High | Amir Hamza | Amir Hamza | 10.30-11.30
139 | Done | 2024-11-05 | Meeting with smart vendor about new join emploee adding in report-TCPL issue | High | Amir Hamza+Rony | Amir Hamza | 11.30-1.00
140 | Done | 2024-11-05 | Training given about opening new GL head-TCPL issue | High | Amir Hamza | Amir Hamza | 2.00-3.00
141 | Done | 2024-11-05 | Mytranscom employee mobile number shown duplicate-TCL issue | High | Tamim+Amir Hamza | Amir Hamza | 3.00-4.00
142 | Done | 2024-11-05 | OKR not found one another 10101378 assaduzamman,13101478 projjol | High | Tamim+Dip+Amir Hamza | Amir Hamza | 4.00-6.00
143 | Done | 2024-11-06 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
144 | Done | 2024-11-06 | Taking All Corporate Application and Database Backup-TCL issue | High | Amir Hamza | Amir Hamza | 10.30-12.00
145 | Done | 2024-11-06 | Payment Bank code for Birulia not found in accpac-TCPL issue | High | Tawhid sir+Amir Hamza | Amir Hamza | 12.00-1.00
146 | Done | 2024-11-06 | Mytranscom employee supervisor changed alright in app team but show in team attendence-SKF issue | High | Tamim+Amir Hamza | Amir Hamza | 2.00-3.30
147 | Done | 2024-11-06 | Mytranscom emploee-mohsin reza attendence not approve supervisor-SKF issue | High | Tamim+Amir Hamza | Amir Hamza | 3.30-4.30
148 | Done | 2024-11-06 | Send back to the integration stage IO-24091034264, 24091034214-PALO issue | High | Amir Hamza | Amir Hamza | 4.30-6.00
149 | Done | 2024-11-07 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
150 | Done | 2024-11-07 | TCPL Non Mgmt. and Casual: Deactivate from portal-TCPL issue | High | Amir Hamza | Amir Hamza | 10.30-12.00
151 | Done | 2024-11-07 | Request to replace the attached report IO-24091034291-PALO issue | High | Dip+Amir Hamza | Amir Hamza | 12.00-1.00
152 | Done | 2024-11-07 | Request to replace the client approval file of this IO-24091034191-PALO issue | High | Dip+Amir Hamza | Amir Hamza | 2.00-2.30
153 | Done | 2024-11-07 | Chorki vedor transaction report-PALO issue | High | Tawhid sir+Amir Hamza | Amir Hamza | 2.30-4.00
154 | Done | 2024-11-08 | IO stage change-PALO issue | High | Amir Hamza | Amir Hamza | 4.00-6.00
155 | Done | 2024-11-10 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
156 | Done | 2024-11-10 | commuinication with PALO IT about C drive space free | High | Tech team+PALO IT | Amir Hamza | 10.30-12.00
157 | Done | 2024-11-10 | IO stage change-PALO issue | High | Amir Hamza | Amir Hamza | 12.00-1.00
158 | Done | 2024-11-10 | GAL attendence device setup with zktecho software system | High | Amir Hamza | Amir Hamza | 2.00-4.00
159 | Done | 2024-11-10 | IO stage change and inventory type change-PALO issue | High | DIp+Amir Hamza | Amir Hamza | 4.00-5.30
160 | Done | 2024-11-10 | Provide TCPL number of active employee and apps user information-TCPL issue | High | Tamim+Amir Hamza | Amir Hamza | 5.30-6.00
161 | Done | 2024-11-11 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
162 | Done | 2024-11-11 | mytranscom user punch record showing bt getting absent mail-SKF issue | High | Tamim+Amir Hamza | Amir Hamza | 10.30-11.30
163 | Done | 2024-11-11 | commuinicate with palo accounts and IT about c drive space-PALO issue | High | Amir Hamza | Amir Hamza | 11.30-1.00
164 | Done | 2024-11-11 |  |  |  | Amir Hamza
165 | Done | 2024-11-11 |  |  |  | Amir Hamza
166 | Done | 2024-11-11 |  |  |  | Amir Hamza
167 | Done | 2024-11-12 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
168 | Done | 2024-11-12 | user create and provide attendence mechine access-GAL issue | High | Tawhid sir+Amir Hamza | Amir Hamza | 10.30-11.30
169 | Done | 2024-11-12 | meeting with palo IT and free c drive space-PALO issue | High | Gazi+Amir Hamza | Amir Hamza | 11.30-1.30
170 | Done | 2024-11-12 | user card no remove from attendence mechine-TBL issue | High | Amir Hamza | Amir Hamza | 2.30-3.30
171 | Done | 2024-11-12 | Changing asset optional field in accpac | High | Jitu+Amir Hamza | Amir Hamza | 3.30-4.30
172 | Done | 2024-11-12 | Commuinicate with palo IT about new RND server and vpn connection issue | High | Amir Hamza | Amir Hamza | 4.30-6.00
173 | Done | 2024-11-13 | PALO server check and take database backup-PALO issue | High | Amir Hamza | Amir Hamza | 9.45-10.30
174 | Done | 2024-11-13 | Taking All Corporate Application and Database Backup-TCL issue | High | Amir Hamza | Amir Hamza | 10.30-12.00
175 | Done | 2024-11-13 |  |  |  | Amir Hamza
| Done | 2024-11-13

## Monthly Checking issue
SL | Issue Name | Date
1 | 10 tk - 12tk Check in Circulation | Every Month 30-31

## Resource Name
SL | Resources
1 | Mr.Tawhid
2 | Afrin
3 | Afrin+Mamun
4 | Salim
5 | Jitu
6 | Salman
7 | Mamun
8 | Amir Hamza

## Important (hidden)
| Afrin | TBL
| Salim | TFL |  |  | Afrin
Done | Nasrin | PALO |  |  | Salim
Pending | Tumpa | TCR |  |  | Nasrin
Working | Salman | TCPL |  | 2023-10-02 | Tumpa
| Fahim | TDCL |  |  | Salman
| Mamun | TEL | 2023-08-09 |  | Fahim
High | Hamza | BLL |  |  | Mamun
Normal | Jitu | THL |  |  | Hamza
| Limon | TCL |  |  | Jitu
| Amir Hamza | Dot birth |  |  | Limon
|  | SKF |  |  | Amir Hamza
All Sister Concern: Smart Attendance System , ZKBIO
All Business Unit (DB Back UP)
VAT System
Attendance
Done
Pending
2023-04-13
2023-04-13
2023-04-13